## BOQ (2)
Sr. No | WBS | Category 1 | Category 2 | Category 3 | Category 4 | Item Description | UOM | Total Scope Quantity | SOR Rate 1 | Payment Breakup %
1 | 1 | Pipeline Laying | Pipeline | Gravity laying |  | Pipe line Earthwork, Supplying, laying and bedding - Supply & Laying of RCC NP3 Hume pipe of 32.312 km including earth work , sand filling, refilling , conveyance of surplus earth, Granular & PCC bedding etc all.
2 | 1.1 | Pipeline Laying | Pipeline | Gravity laying |  | 150 mm dia. RCC sewers | Meter | 20135.66 | 2499.6271
3 | 1.1.1 | Pipeline Laying | Pipeline | Gravity laying | Supply | On Supply of Pipe |  | 20135.66 | 2499.6271 | 30%
4 | 1.1.2 | Pipeline Laying | Pipeline | Gravity laying | Execution | On Completion of Laying of Pipeline |  | 20135.66 | 2499.6271 | 60%
5 | 1.1.3 | Pipeline Laying | Pipeline | Gravity laying | Testing & Commissioning | Testing & Commissioning |  | 20135.66 | 2499.6271 | 10%
6 | 1.2 | Pipeline Laying | Pipeline | Gravity laying |  | 200 mm dia. RCC sewers | Meter | 46026.4 | 3183.6692
7 | 1.2.1 | Pipeline Laying | Pipeline | Gravity laying | Supply | On Supply of Pipe |  | 46026.4 | 3183.6692 | 30%
8 | 1.2.2 | Pipeline Laying | Pipeline | Gravity laying | Execution | On Completion of Laying of Pipeline |  | 46026.4 | 3183.6692 | 60%
9 | 1.2.3 | Pipeline Laying | Pipeline | Gravity laying | Testing & Commissioning | Testing & Commissioning |  | 46026.4 | 3183.6692 | 10%
10 | 1.3 | Pipeline Laying | Pipeline | Gravity laying |  | 250 mm dia. RCC sewers | Meter | 1809.4 | 5800.0286
11 | 1.3.1 | Pipeline Laying | Pipeline | Gravity laying | Supply | On Supply of Pipe |  | 1809.4 | 5800.0286 | 30%
12 | 1.3.2 | Pipeline Laying | Pipeline | Gravity laying | Execution | On Completion of Laying of Pipeline |  | 1809.4 | 5800.0286 | 60%
13 | 1.3.3 | Pipeline Laying | Pipeline | Gravity laying | Testing & Commissioning | Testing & Commissioning |  | 1809.4 | 5800.0286 | 10%
14 | 1.4 | Pipeline Laying | Pipeline | Gravity laying |  | 300 mm dia. RCC sewers | Meter | 538.9
15 | 1.4.1 | Pipeline Laying | Pipeline | Gravity laying | Supply | On Supply of Pipe |  | 538.9 | 0 | 30%
16 | 1.4.2 | Pipeline Laying | Pipeline | Gravity laying | Execution | On Completion of Laying of Pipeline |  | 538.9 | 0 | 60%
17 | 1.4.3 | Pipeline Laying | Pipeline | Gravity laying | Testing & Commissioning | Testing & Commissioning |  | 538.9 | 0 | 10%
18 | 1.5 | Pipeline Laying | Pipeline | Gravity laying |  | 350 mm dia. RCC sewers | Meter | 78
19 | 1.5.1 | Pipeline Laying | Pipeline | Gravity laying | Supply | On Supply of Pipe |  | 78 | 0 | 30%
20 | 1.5.2 | Pipeline Laying | Pipeline | Gravity laying | Execution | On Completion of Laying of Pipeline |  | 78 | 0 | 60%
21 | 1.5.3 | Pipeline Laying | Pipeline | Gravity laying | Testing & Commissioning | Testing & Commissioning |  | 78 | 0 | 10%
22 | 2 | Civil | Chamber | Manhole Chamber |  | Supplying all materials and labour and construction of Manhole Chambers and drop manholes as per approved design & specification, including leakage testing of chambers
23 | 2.1 | Civil | Chamber | Manhole Chamber |  | On completion of construction of circular manhole 900 mm internal dia upto 1.65 m depth Brick Masonry Man Hole Chambers | No.s | 2335 | 24432.9916
24 | 2.1.1 | Civil | Chamber | Manhole Chamber | Execution | On completion of construction |  | 2335 | 24432.9916 | 90%
25 | 2.1.2 | Civil | Chamber | Manhole Chamber | Testing & Commissioning | Testing & Commissioning |  | 2335 | 24432.9916 | 10%
26 | 2.2 | Civil | Chamber | Manhole Chamber |  | On completion of construction of circular manhole 1200 mm internal dia corbelling in shape at top and brick work upto 1.5 m and above 1.65 m and upto 2.30 m depth RCC work as per standard drawing | No.s | 1996 | 61371.9428
27 | 2.2.1 | Civil | Chamber | Manhole Chamber | Execution | On completion of construction |  | 1996 | 61371.9428 | 90%
28 | 2.2.2 | Civil | Chamber | Manhole Chamber | Testing & Commissioning | Testing & Commissioning |  | 1996 | 61371.9428 | 10%
29 | 2.3 | Civil | Chamber | Manhole Chamber |  | On completion of construction of circular manhole 1500 mm internal dia corbelling in shape at top and brick work upto 1.5 m and above 2.30 m and above depth RCC work as per standard drawing | No.s | 1102 | 112711.1738
30 | 2.3.1 | Civil | Chamber | Manhole Chamber | Execution | On completion of construction |  | 1102 | 112711.1738 | 90%
31 | 2.3.2 | Civil | Chamber | Manhole Chamber | Testing & Commissioning | Testing & Commissioning |  | 1102 | 112711.1738 | 10%
32 | 3 | Civil | Road Cutting & Restoration | Road Cutting & Restoration |  | Road Cutting & Restoration
33 | 3.1 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Cutting -Dismantling boulders including T&P, sorting the dis-mantled material disposal of unserviceable material & stacking the serviceable material with all lift & lead | cum | 5178 | 261.0368 | 100%
34 | 3.2 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Cutting -Dismantling and bituminous courses of flexible pavement and disposal of dismantled material and staking the serviceable material with all lifts and lead and other incidental and operational charges etc., as per directions of engineer in charge | cum | 1246 | 852.335 | 100%
35 | 3.3 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Cutting - Dismantling of cement concrete grade M-15& M 20 including T&P, sorting the dismantled material, disposal of un serviceable material and staking the serviceable material with all lifts and lead and other incidental and operational charges etc., as per directions of engineer in charge | cum | 14380 | 1638.1989 | 100%
36 | 3.4 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Cutting - Dismantling of paver block including T&P ,sorting the dismantled material, disposal of un serviceable material and staking the serviceable material with all lifts and lead and other incidental and operational charges etc., as per directions of engineer in charge | sqm | 33926 | 73.9906 | 100%
37 | 3.5 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Restoration-Metalled Road complete as per specification | cum | 5178 | 2256.1034 | 100%
38 | 3.6 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Restoration-Bitumen Road complete as per specification | cum | 1246 | 3796.765 | 100%
39 | 3.7 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Restoration - Cement Concrete Road complete as per specification | cum | 14380 | 6492.3701 | 100%
40 | 3.8 | Civil | Road Cutting & Restoration | Road Cutting & Restoration | Execution | Road Restoration - Paver block complete as per specification (50% New +50% Re-use) | sqm | 33926 | 480.9387 | 100%
41 | 4 | Pipeline Laying | Pipeline | Water Supply Pipeline | Execution | Miscellaneous like dismantling and reinstating utilities like water supply and drainage
42 | 4.1 | Pipeline Laying | Pipeline | Water Supply Pipeline |  | Reinstatement of Water Supply Pipe lines
43 | 4.1.1 | Pipeline Laying | Pipeline | Water Supply Pipeline |  | Supply delivery and conveying the following size of CI/DI LA class S/S pipes and specials etc. to the site, lowering, aligning, laying, jointing and testing of water supply pipe line including shoring and shuttering, bailing out water, dewatering, earth work excavation in all kinds of soil and road layers encountered, refilling with excavated earth, disposing of surplus material, making good to the damages of the service utilities, barricading, lighting, watch & ward etc. including supply of all labour, T & P , taxes , transportation and incidental charges thereof as required depth all complete as per approved drawing and specifications and direction of Engineer-in-Charge.
44 | 4.1.1.1 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 100mm | Meter | 933.41 | 1257.2908 | 100%
45 | 4.1.1.2 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 150mm | Meter | 153.55 | 1806.381 | 100%
46 | 4.1.1.3 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 200mm | Meter | 144.55 | 2249.914 | 100%
47 | 4.1.1.4 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 250mm | Meter | 117.7 | 2985.3876 | 100%
48 | 4.1.2 | Pipeline Laying | Pipeline | Water Supply Pipeline |  | Supply delivery and conveying the following size of uPVC pipes and specials etc. to the site, lowering, aligning, laying, jointing and testing of water supply pipe line including shoring and shuttering, bailing out water, dewatering, earth work excavation in all kinds of soil and road layers encountered, refilling with excavated earth, disposing of surplus material, making good to the damages of the service utilities, barricading, lighting, watch & ward etc. including supply of all labour, T & P , taxes ,transportation and incidental charges thereof as required depth all complete as per approved drawing and specifications and direction of Engineer-in-Charge.
49 | 4.1.2.1 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 25mm | Meter | 1185 | 154.5468 | 100%
50 | 4.1.2.2 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 40mm | Meter | 1066 | 280.5062 | 100%
51 | 4.1.2.3 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 100 mm | Meter | 500 | 379.9276 | 100%
52 | 4.1.2.4 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 150 mm | Meter | 263 | 742.6639 | 100%
53 | 4.1.3.5 | Pipeline Laying | Pipeline | Water Supply Pipeline | Supply | 200 mm | Meter | 154 |  | 100%
54 | 4.2 | Civil | Other Civil Work | Drains | Execution | Repair of municipality drains: Dismantling brick or stone masonry in cement mortar, concrete upto 3 m depth below ground level including stacking the useful material for reuse and removing the debris as per the direction of Engineer-in-Charge. Reinstating municipality storm water drains of 600x600mm, inside with RCC M20 necessary excavation foundation concrete 1:3:6 (1cement:3 fine sand:6 graded stone aggregate 40 mm nominal size) including shoring and shuttering, bailing out water, dewatering, earth work excavation in all kinds of soil and road layers encountered, refilling with excavated earth, disposing of surplus material, barricading, lighting, watch & ward etc. as per standard design drawing including supply of labour, T & P as required all complete as per the direction of Engineer-in-charge. | Meter | 12723 | 3009.3661 | 100%
55 | 4.3 | Civil | Other Civil Work | Reinstatement of Existing Culverts | Execution | Reinstatement of Existing Culverts :Dismantling of Reinforced cement concrete with cleaning, straightening and cutting of bars and separating out from RCC in foundation and/or upto 1.5 mts above ground level including sorting the dismantled materials, disposal of unserviceable materials, stacking the serviceable materials providing and removing scaffolding wherever necessary etc., complete as per standard detailed technical specifications and approved design and drawings and any other incidental charges, hire charges of machinaries, loading and unloading charges with all lead and lift and as directed by the Engineer-in-charge. | No.s | 45 | 743406.587 | 100%
56 | 5 | Pipeline Laying | Pipeline | Construction of House Sewers | Execution | Construction of House Sewers (110mm dia UPVC S/S) as per approved drawings and specification – 3486 Nos. (appx) 17430m (appx) |  | 0
57 | 5.1 | Pipeline Laying | Pipeline | Construction of House Sewers |  | Supply, delivery at site the following size of ISI marked UPVC S/S house sewer pipes of 110 mm diameter and rubber ring gasket and all other materials, labour, T & P, and lowering the pipes in to the trench, aligning, laying to approved level or slope, jointing, testing and commissioning of sewer line including earth work in excavation in all kinds of soil and all types of road encountered during cutting, required, laying of cement concrete cradle in M 15 grade (1:2:4) using 12 mm gauge hard broken granite chips in Type A bedding (IS: 783-1985), refilling with excavated earth, disposing of surplus material, barricading, lighting, watch and ward including all taxes, royality, transportation and incidental charges thereof etc. all complete as per IS/PH specification and approved drawing and direction of Engineer-in-charge, upto an average depth of (from Ground Level to invert) | Meter | 37000 | 1971.9155
58 | 5.1.1 | Pipeline Laying | Pipeline | House sewer pipes | Execution | On completion of laying as per sepcification complete in all respect |  | 37000 | 1971.9155 | 90%
59 | 5.1.2 | Pipeline Laying | Pipeline | House sewer pipes | Testing & Commissioning | Testing & Commissioning |  | 37000 | 1971.9155 | 10%
60 | 5.2 | Civil | chamber | HSC Chamber |  | Constructing inspection chamber 600x600x400mm, inside Brick work with Fly Ash bricks 23cm x 11cm x 8cm in cement mortar 1:5 (1 cement : 5 coarse sand) for sewage collection from the house sewer complete with RCC top slab 1:4:8 mix (1 cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) necessary excavation foundation concrete 1:2:4 (1 cement: 2 fine sand: 4 graded stone aggregate 40 mm nominal size) and inside & outside plastering with cement mortar 1:3 (1 cement : 3 coarse sand) 12 mm thick finished with Plain Cement Concrete (1:1/2:3) with 12mm stone ballast in benching complete as per standard design drawing including supply of labour, T & P as required all complete as per the direction of Engineer-in-charge. (3486 Nos. | No.s | 7400 | 11008.9381
61 | 5.2.1 | Civil | chamber | HSC Chamber | Execution | On completion of laying as per sepcification complete in all respect |  | 7400 | 11008.9381 | 90%
62 | 5.2.2 | Civil | chamber | HSC Chamber | Testing & Commissioning | Testing & Commissioning |  | 7400 | 11008.9381 | 10%
63 | 6.1 | Civil | SPS | SPS 01 |  | Construction of Sewage Pumping Stations |  | 0
64 | 6.1.1 | Civil | SPS | SPS 00 |  | Construction of 2.0 mtr dia wetwell cum pumphouse | No.s | 2 | 1786106.735
65 | 6.1.1.1 | Civil | SPS | SPS 01 | Execution | On completion of RCC structure complete in all respect as per specification |  | 2 | 1786106.735 | 45%
66 | 6.1.1.2 | Civil | SPS | SPS 01 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 2 | 1786106.735 | 45%
67 | 6.1.1.3 | Civil | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 1786106.735 | 10%
68 | 6.1.2 | Civil | SPS | SPS 01 |  | Construction of Valve chamber | No.s | 2 | 144819.465
69 | 6.1.2.1 | Civil | SPS | SPS 01 | Execution | On completion of RCC works complete in all respect as per specification |  | 2 | 144819.465 | 45%
70 | 6.1.2.2 | Civil | SPS | SPS 01 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 2 | 144819.465 | 45%
71 | 6.1.2.3 | Civil | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 144819.465 | 10%
72 | 6.1.3 | Civil | SPS | SPS 01 |  | Construction of Inlet chamber, screen chamber | No.s | 2 | 531004.705
73 | 6.1.3.1 | Civil | SPS | SPS 01 | Execution | On completion of RCC works complete in all respect as per specification |  | 2 | 531004.705 | 45%
74 | 6.1.3.2 | Civil | SPS | SPS 01 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 2 | 531004.705 | 45%
75 | 6.1.3.3 | Civil | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 531004.705 | 10%
76 | 6.1.4 | E&M | SPS | SPS 01 |  | Piping and mechanical works | No.s | 2 | 2268838.285
77 | 6.1.4.1 | E&M | SPS | SPS 01 | Execution | On supply of Piping and mechanical equipments as per specification |  | 2 | 2268838.285 | 45%
78 | 6.1.4.2 | E&M | SPS | SPS 01 | Execution | On completion of Installation- complete in all respect |  | 2 | 2268838.285 | 45%
79 | 6.1.4.3 | E&M | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 2268838.285 | 10%
80 | 6.1.5 | Civil | SPS | SPS 01 |  | Formation of Site Formation,Service Road,approach Road | No.s | 2 | 241365.775
81 | 6.1.5.1 | Civil | SPS | SPS 01 | Execution | Site formation complete as per specification |  | 2 | 241365.775 | 60%
82 | 6.1.5.2 | Civil | SPS | SPS 01 | Execution | Service road complete as per requirement |  | 2 | 241365.775 | 30%
83 | 6.1.5.3 | Civil | SPS | SPS 01 | Execution | Approach road complete in all respect as per specification |  | 2 | 241365.775 | 10%
84 | 6.1.6.1 | Civil | SPS | SPS 01 |  | Construction of Compound Wall | No.s | 2 | 1544740.96
85 | 6.1.6.1.1 | Civil | SPS | SPS 01 | Execution | On completion of foundation, RCC/Brick wall complete as per specification |  | 2 | 1544740.96 | 60%
86 | 6.1.6.1.2 | Civil | SPS | SPS 01 | Execution | On completion of plastering, painting, gate fixing etc complete as per specification |  | 2 | 1544740.96 | 40%
87 | 6.1.7 | Civil | SPS | SPS 01 |  | Construction of DG Room | No.s | 2 | 724097.325
88 | 6.1.7.1 | Civil | SPS | SPS 01 | Execution | On completion of structural works as per specfication |  | 2 | 724097.325 | 50%
89 | 6.1.7.2 | Civil | SPS | SPS 01 | Execution | On completion of all finishes complete after installation of DG and it's accessories as per specification |  | 2 | 724097.325 | 50%
90 | 6.1.8 | Civil | SPS | SPS 01 |  | Construction of MCC cum office room | No.s | 2 | 917189.945
91 | 6.1.8.1 | Civil | SPS | SPS 01 | Execution | On completion of structural works as per specfication |  | 2 | 917189.945 | 50%
92 | 6.1.8.2 | Civil | SPS | SPS 01 | Execution | On completion of all finishes complete after installation of all equipment and it's accessories as per specification |  | 2 | 917189.945 | 50%
93 | 6.1.9 | E&M | SPS | SPS 01 |  | Electrical works | No.s | 2 | 2172291.975
94 | 6.1.9.1 | E&M | SPS | SPS 01 | Supply | On supply of Electrical equipments as per specification |  | 2 | 2172291.975 | 60%
95 | 6.1.9.2 | E&M | SPS | SPS 01 | Execution | On completion of Installation- complete in all respect |  | 2 | 2172291.975 | 30%
96 | 6.1.9.3 | E&M | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 2172291.975 | 10%
97 | 6.1.10 | E&M | SPS | SPS 01 |  | DG set with AMF Pannel | No.s | 2 | 1544740.96
98 | 6.1.10.1 | E&M | SPS | SPS 01 | Supply | On supply of DG set with AMF panel as per specification |  | 2 | 1544740.96 | 60%
99 | 6.1.10.2 | E&M | SPS | SPS 01 | Execution | On completion of Installation- complete in all respect |  | 2 | 1544740.96 | 30%
100 | 6.1.10.3 | E&M | SPS | SPS 01 | Testing & Commissioning | Completion of Testing & commissioning |  | 2 | 1544740.96 | 10%
101 | 6.2 | Civil | SPS | SPS 02 |  | SPS - 02 | No.s | 0 | 1544740.96
102 | 6.2.1 | Civil | SPS | SPS 02 |  | Construction of 3.5 mtr dia wetwell cum pumphouse | No.s | 1
103 | 6.2.1.1 | Civil | SPS | SPS 02 | Execution | On completion of RCC structure complete in all respect as per specification |  | 1 | 0 | 45%
104 | 6.2.1.2 | Civil | SPS | SPS 02 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 1 | 0 | 45%
105 | 6.2.1.3 | Civil | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
106 | 6.2.2 | Civil | SPS | SPS 02 |  | Construction of Valve chamber | No.s | 1
107 | 6.2.2.1 | Civil | SPS | SPS 02 | Execution | On completion of RCC works complete in all respect as per specification |  | 1 | 0 | 45%
108 | 6.2.2.2 | Civil | SPS | SPS 02 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 1 | 0 | 45%
109 | 6.2.2.3 | Civil | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
110 | 6.2.3 | Civil | SPS | SPS 02 |  | Construction of Inlet chamber, screen chamber | No.s | 1
111 | 6.2.3.1 | Civil | SPS | SPS 02 | Execution | On completion of RCC works complete in all respect as per specification |  | 1 | 0 | 45%
112 | 6.2.3.2 | Civil | SPS | SPS 02 | Execution | On completion of all finishes complete after installation of all equipments as per specification |  | 1 | 0 | 45%
113 | 6.2.3.3 | Civil | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
114 | 6.2.4 | E&M | SPS | SPS 02 |  | Piping and mechanical works | No.s | 1
115 | 6.2.4.1 | E&M | SPS | SPS 02 | Supply | On supply of Piping and mechanical equipments as per specification |  | 1 | 0 | 45%
116 | 6.2.4.2 | E&M | SPS | SPS 02 | Execution | On completion of Installation- complete in all respect |  | 1 | 0 | 45%
117 | 6.2.4.3 | E&M | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
118 | 6.2.5 | E&M | SPS | SPS 02 |  | Formation of Site Formation,Service Road,approach Road | No.s | 1
119 | 6.2.5.1 | Civil | SPS | SPS 02 | Execution | Site formation complete as per specification |  | 1 | 0 | 60%
120 | 6.2.5.2 | Civil | SPS | SPS 02 | Execution | Service road complete as per requirement |  | 1 | 0 | 30%
121 | 6.2.5.3 | Civil | SPS | SPS 02 | Execution | Approach road complete in all respect as per specification |  | 1 | 0 | 10%
122 | 6.2.6.2 | Civil | SPS | SPS 02 |  | Construction of Compound Wall | No.s | 1
123 | 6.2.6.2.1 | Civil | SPS | SPS 02 | Execution | On completion of foundation, RCC/Brick wall complete as per specification |  | 1 | 0 | 60%
124 | 6.2.6.2.2 | Civil | SPS | SPS 02 | Execution | On completion of plastering, painting, gate fixing etc complete as per specification |  | 1 | 0 | 40%
125 | 6.2.7 | Civil | SPS | SPS 02 |  | Construction of DG Room | No.s | 1
126 | 6.2.7.1 | Civil | SPS | SPS 02 | Execution | On completion of structural works as per specfication |  | 1 | 0 | 50%
127 | 6.2.7.2 | Civil | SPS | SPS 02 | Execution | On completion of all finishes complete after installation of DG and it's accessories as per specification |  | 1 | 0 | 50%
128 | 6.2.8 | Civil | SPS | SPS 02 |  | Construction of MCC cum office room | No.s | 1
129 | 6.2.8.1 | Civil | SPS | SPS 02 | Execution | On completion of structural works as per specfication |  | 1 | 0 | 50%
130 | 6.2.8.2 | Civil | SPS | SPS 02 | Execution | On completion of all finishes complete after installation of all equipment and it's accessories as per specification |  | 1 | 0 | 50%
131 | 6.2.9 | E&M | SPS | SPS 02 |  | Electrical works | No.s | 1
132 | 6.2.9.1 | E&M | SPS | SPS 02 | Supply | On supply of Electrical equipments as per specification |  | 1 | 0 | 60%
133 | 6.2.9.2 | E&M | SPS | SPS 02 | Execution | On completion of Installation- complete in all respect |  | 1 | 0 | 30%
134 | 6.2.9.3 | E&M | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
135 | 6.2.10 | E&M | SPS | SPS 02 |  | DG set with AMF Pannel | No.s | 1
136 | 6.2.10.1 | E&M | SPS | SPS 02 | Supply | On supply of DG set with AMF panel as per specification |  | 1 | 0 | 60%
137 | 6.2.10.2 | E&M | SPS | SPS 02 | Execution | On completion of Installation- complete in all respect |  | 1 | 0 | 30%
138 | 6.2.10.3 | E&M | SPS | SPS 02 | Testing & Commissioning | Completion of Testing & commissioning |  | 1 | 0 | 10%
139 | 7 | Civil | MPS | MPS |  | Construction of Manhole Pumping Stations | No.s | 4 | 4344583.95
140 | 7.1 | Civil | MPS | MPS |  | Construction of Manhole Pumping Stations (Civil Work)
141 | 7.1.1 | Civil | MPS | MPS | Execution | On completion of 50% of the RCC structure of MHPS |  | 0 | 0 | 15%
142 | 7.1.2 | Civil | MPS | MPS | Execution | On completion of balance 50% of the RCC structure of MHPS |  | 0 | 0 | 15%
143 | 7.1.3 | Civil | MPS | MPS | Execution | On completion of all finishing works, after installation of all required electro-mechanical equipments, and completion of all related structures of MHPS complete in all respect as per specification - of MHPS |  | 0 | 0 | 20%
144 | 7.2 | E&M | MPS | MPS |  | Electro-Mechanical Work for Manhole Pumping Stations
145 | 7.2.1 | E&M | MPS | MPS | Supply | On supply of all required Mechanical, electrical , instrumentation Items for Manhole Pumping Stations - all equipments complete as per specification. |  | 0 | 0 | 30%
146 | 7.2.2 | E&M | MPS | MPS | Execution | On completion of installations of all required Mechanical, electrical, instrumention Items of MHPS |  | 0 | 0 | 10%
147 | 7.2.3 | E&M | MPS | MPS | Testing & Commissioning | Testing & Commissioning complete in all respect as per specification of MHPS |  | 0 | 0 | 10%
148 | 8 | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising main DI K9 pipe |  | 0
149 | 8.1 | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising Mains DI K9 300mm dia | Meter | 250 | 6758.2417
150 | 8.1.1 | Pipeline Laying | Pipeline | Raising Main | Supply | On Completion of Supply of DI-K9 Pipe |  | 250 | 6758.2417 | 60%
151 | 8.1.2 | Pipeline Laying | Pipeline | Raising Main | Execution | On Completion of Laying of Pipeline as per specification, complete in all respect |  | 250 | 6758.2417 | 30%
152 | 8.1.3 | Pipeline Laying | Pipeline | Raising Main | Testing & Commissioning | Testing & Commissioning |  | 250 | 6758.2417 | 10%
153 | 8.2 | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising Mains DI K9 250 mm dia | Meter | 660
154 | 8.2.1 | Pipeline Laying | Pipeline | Raising Main | Supply | On Completion of Supply of DI-K9 Pipe |  | 660 | 0 | 60%
155 | 8.2.2 | Pipeline Laying | Pipeline | Raising Main | Execution | On Completion of Laying of Pipeline as per specification, complete in all respect |  | 660 | 0 | 30%
156 | 8.2.3 | Pipeline Laying | Pipeline | Raising Main | Testing & Commissioning | Testing & Commissioning |  | 660 | 0 | 10%
157 | 8.3 | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising Mains DI K9 150 mm dia | Meter | 1386
158 | 8.3.1 | Pipeline Laying | Pipeline | Raising Main | Supply | On Completion of Supply of DI-K9 Pipe |  | 1386 | 0 | 60%
159 | 8.3.2 | Pipeline Laying | Pipeline | Raising Main | Execution | On Completion of Laying of Pipeline as per specification, complete in all respect |  | 1386 | 0 | 30%
160 | 8.3.3 | Pipeline Laying | Pipeline | Raising Main | Testing & Commissioning | Testing & Commissioning |  | 1386 | 0 | 10%
161 | 8.4 | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising Mains DI K9 100 mm dia | Meter | 130 | 4827.3155
162 | 8.4.1 | Pipeline Laying | Pipeline | Raising Main | Supply | On Completion of Supply of DI-K9 Pipe |  | 130 | 4827.3155 | 60%
163 | 8.4.2 | Pipeline Laying | Pipeline | Raising Main | Execution | On Completion of Laying of Pipeline as per specification, complete in all respect |  | 130 | 4827.3155 | 30%
164 | 8.4.3 | Pipeline Laying | Pipeline | Raising Main | Testing & Commissioning | Testing & Commissioning |  | 130 | 4827.3155 | 10%
165 | 8.4A | Pipeline Laying | Pipeline | Raising Main |  | Laying of Rising Mains DI K9 100 mm dia | Meter | 170
166 | 8.4A.1 | Pipeline Laying | Pipeline | Raising Main | Supply | On Completion of Supply of DI-K9 Pipe |  | 170 | 0 | 60%
167 | 8.4A.2 | Pipeline Laying | Pipeline | Raising Main | Execution | On Completion of Laying of Pipeline as per specification, complete in all respect |  | 170 | 0 | 30%
168 | 8.4A.3 | Pipeline Laying | Pipeline | Raising Main | Testing & Commissioning | Testing & Commissioning |  | 170 | 0 | 10%
169 | 9 | Pipeline Laying | Pipeline | Trenchless laying |  | On supplying Jacking quality Sulphate resistant RCC pipes suitable for micro tunneling and all other materials required; and Laying of Sewers by Trenchless method using micro tunneling process (150 mm to 200mm dia)-93 m (appx.) |  | 0
170 | 9.1 | Pipeline Laying | Pipeline | Trenchless laying |  | On completion of laying and testing of 150 mm dia of sewer line | Meter | 81 | 86891.679
171 | 9.1.1 | Pipeline Laying | Pipeline | Trenchless laying | Supply | On Supply and laying of RCC Jacking Pipe as per specifications, complete in all respect |  | 81 | 86891.679 | 90%
172 | 9.1.2 | Pipeline Laying | Pipeline | Trenchless laying | Testing & Commissioning | Testing & Commissioning |  | 81 | 86891.679 | 10%
173 | 9.2 | Pipeline Laying | Pipeline | Trenchless laying |  | On completion of laying and testing of 200 mm dia of sewer line | Meter | 82 | 86489.4027
174 | 9.2.1 | Pipeline Laying | Pipeline | Trenchless laying | Supply | On Supply and laying of RCC Jacking Pipe as per specifications, complete in all respect |  | 82 | 86489.4027 | 90%
175 | 9.2.2 | Pipeline Laying | Pipeline | Trenchless laying | Testing & Commissioning | Testing & Commissioning |  | 82 | 86489.4027 | 10%
176 | 9.3 | Pipeline Laying | Pipeline | Trenchless laying |  | On completion of laying and testing of 300 mm dia of sewer line |  | 32
177 | 9.3.1 | Pipeline Laying | Pipeline | Trenchless laying | Supply | On Supply and laying of RCC Jacking Pipe as per specifications, complete in all respect |  | 32 | 0 | 90%
178 | 9.3.2 | Pipeline Laying | Pipeline | Trenchless laying | Testing & Commissioning | Testing & Commissioning |  | 32 | 0 | 10%
179 | 9.4 | Pipeline Laying | Pipeline | Trenchless laying |  | On completion of laying and testing of 350 mm dia of sewer line |  | 34
180 | 9.4.1 | Pipeline Laying | Pipeline | Trenchless laying | Supply | On Supply and laying of RCC Jacking Pipe as per specifications, complete in all respect |  | 34 | 0 | 90%
181 | 9.4.2 | Pipeline Laying | Pipeline | Trenchless laying | Testing & Commissioning | Testing & Commissioning |  | 34 | 0 | 10%
182 | 10 | E&M | Equipments | Machine & Equipment | Supply | Sewer cleaning Equipment |  | 0
183 | 10.1 | E&M | Equipments | Machine & Equipment | Supply | Hand operated winching machine | No.s | 2 | 434458.395 | 100%
184 | 10.2 | E&M | Equipments | Machine & Equipment | Supply | Power Rodding Machine | No.s | 2 | 337912.085 | 100%
185 | 10.3 | E&M | Equipments | Machine & Equipment | Supply | Pull Through | No.s | 2 | 96546.31 | 100%
186 | 10.4 | E&M | Equipments | Machine & Equipment | Supply | CCTV Equipment | No.s | 2 | 917189.945 | 100%
187 | 10.5 | E&M | Equipments | Machine & Equipment | Supply | Truck Mounted Jetting Machine | No.s | 2 | 241365.775 | 100%
188 | 10.6 | E&M | Equipments | Machine & Equipment | Supply | Miscellaneous Equipment | No.s | 2 | 965463.1 | 100%
189 | 11 | Drawing & Design | Drawing & Design | Drawing & Design | Supply | Detailed engineering drawing & design and Survey | Lot | 2 | 4827315.5
190 | 11.1 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | Details Survey, topography study & soil Investigation, bench marks, etc of the new network and it's connection to the existing network. |  | 2 | 4827315.5 | 25%
191 | 11.2 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | On approval of Design & Drawing of Gravity sewer of RCC pipe. Design complete in all respect (including connections to the existing network) |  | 2 | 4827315.5 | 15%
192 | 11.3 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | On approval of Design & Drawing of sewer network of Rising main. Design complete in all respect AND |  | 2 | 4827315.5 | 10%
193 | 11.4 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | On approval of Design & Drawing of sewer network by Trenchless Technology. Design complete in all respect, including all required approvals from concern departments. |  | 2 | 4827315.5 | 15%
194 | 11.5 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | On approval of Design & Drawing of all components of Manhole Pumping Station including pumping machineries, electrical equipments, panel board, and all other accessories required for the work- as per specification. Design approval complete in all respect |  | 2 | 4827315.5 | 10%
195 | 11.6 | Drawing & Design | Drawing & Design | Drawing & Design | Details Survey | On approval of As built drawings complete for entire project, completion of Trial run Test of entire network, submission of O&M manual etc, complete in all respect. |  | 2 | 4827315.5 | 25%